## Лист1
branche | taskname | tasknumber | depended with tasknumber | millestone/version | status
web | Localization | 38 |  | w0.9a1.3d1.2m0.0 | canceled
web | Restore subscriber's password | 39 | 40,42,43 | w0.10a1.4d1.3m0.0 | done
api | Restore subscriber's password | 43 | 40 | w0.10a1.4d1.3m0.0 | done
db | Restore subscriber's password | 40 |  | w0.10a1.4d1.3m0.0 | done
api | ws-mvs-login. Validation annotations | 42 |  | w0.10a1.4d1.3m0.0 | done
api | ws-mvs-vehicle. Initialize new project and web-service. | 60 |  | w0.12a1.6d1.4m0.0 | issue created
api | ws-mvs-vehicle. Connect web-servive with Heroku DB | 61 | 60 | w0.12a1.6d1.4m0.0 | issue created
web | Add buttons: add new mileage, add new service invoice, new servive report(pdf) | 62 |  | w0.12a1.6d1.4m0.0 | issue created
web | Modify workdesk | 63 |  | w0.12a1.6d1.4m0.0 | issue created
web | Change subscriber's password from workdesk | 52 | 53.54 | w0.11a1.5d1.4m0.0 | done
api | Change subscriber's password. Improve ws-ms-login | 53 | 54 | w0.11a1.5d1.4m0.0 | done
db | Change subscriber's password. New db functions | 54 |  | w0.11a1.5d1.4m0.0 | done